## Dev1
Project
Source Environment | SQL Server: SF_Migration
Target Environment | NPC_TARGET_v2
Git Repository | https://github.com/jpziller/DataMigration
Commit / Branch | 8bec5b4b (attempt/2026-07-21-npc-dogfood-v2)
Scripts (as of this commit) | https://github.com/jpziller/DataMigration/tree/8bec5b4b7063710fa149a891759db3633b933d1a/attempts/2026-07-21-npc-dogfood-v2/sql
JIRA Project
Last Synced Log Id | 120
Last Synced Source Ingestion Log Id
Stage | Object | Dependency | Status | Critical | Person Responsible | Begin Time | End Time | Execution Time | JIRA Ticket Link | Notes | Total Records | Success Records | Failed Records | Success Percent | Error Details
Pre-Migration Steps
Salesforce Config Changes | Confirm Email Deliverability setting (Setup > Email Administration > Deliverability) | None | Not Started | Yes
Salesforce Config Changes | Disable CPQ/Billing automation (or other managed-package automation) on target objects | None | Not Started | Yes
Salesforce Config Changes | Disable outbound automation that could email real contacts (workflow/Flow email alerts, approval processes) | None | Not Started | Yes
Pre Migration | Confirm target org/alias and auth mode for this pass | None | Not Started | Yes
Pre Migration | Run analyze-org-risk against in-scope objects | None | Not Started | No
Pre Migration | Take a backup/export of any target data being overwritten | None | Not Started | No
Source Download and Load Steps
Load Steps
Load | 130_npc_campaign_load.sql | None; parallel with: GiftDesignation | Completed |  | Jim Ziller | 2026-07-17 20:29 | 2026-07-17 20:29 |  |  | Auto-synced from dbo.BulkOpsLog #15 (insert, 1 job(s)). | 2 | 0 | 0 | 0%
Load | 150_npc_giftdesignation_load.sql | None; parallel with: Campaign | Completed |  | Jim Ziller | 2026-07-17 20:45 | 2026-07-17 20:46 |  |  | Auto-synced from dbo.BulkOpsLog #18 (insert, 1 job(s)). | 2 | 0 | 0 | 0%
Load | 090_npc_household_account_load.sql | After: Contact; parallel with: AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-17 20:26 | 2026-07-17 20:26 |  |  | Auto-synced from dbo.BulkOpsLog #11 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
Load | 110_npc_accountcontactrelation_load.sql | After: Account, Contact; parallel with: Account, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-17 20:28 | 2026-07-17 20:29 |  |  | Auto-synced from dbo.BulkOpsLog #13 (insert, 1 job(s)). | 8 | 0 | 0 | 0%
Load | 340_campaignmember_load.sql | After: Account, Campaign, Contact; parallel with: Account, AccountContactRelation, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-17 16:40 | 2026-07-17 16:40 |  |  | Auto-synced from dbo.BulkOpsLog #6 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
Load | 020_contact_load.sql | After: Account; parallel with: Account, AccountContactRelation, CampaignMember, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-14 18:55 | 2026-07-14 18:55 |  |  | Auto-synced from dbo.BulkOpsLog #1 (upsert, 1 job(s)). | 8 | 8 | 0 | 100%
Load | 270_contactcontactrelation_load.sql | After: Contact; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-19 14:11 | 2026-07-19 14:11 |  |  | Auto-synced from dbo.BulkOpsLog #43 (insert, 1 job(s)). | 5 | 0 | 0 | 0%
Load | 300_contactpointaddress_load.sql | After: Account, ContactPointPhone; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-19 15:51 | 2026-07-19 15:51 |  |  | Auto-synced from dbo.BulkOpsLog #50 (insert, 1 job(s)). | 35 | 0 | 0 | 0%
Load | 320_contactpointemail_load.sql | After: Account; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-19 17:47 | 2026-07-19 17:47 |  |  | Auto-synced from dbo.BulkOpsLog #53 (insert, 1 job(s)). | 35 | 35 | 0 | 100%
Load | 310_contactpointphone_load.sql | After: Account; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-19 17:45 | 2026-07-19 17:46 |  |  | Auto-synced from dbo.BulkOpsLog #52 (insert, 1 job(s)). | 35 | 35 | 0 | 100%
Load | 160_npc_giftcommitment_from_rd_load.sql | After: Account, Campaign, GiftCommitmentSchedule; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Issue |  | Jim Ziller | 2026-07-17 20:55 | 2026-07-17 20:55 |  |  | Auto-synced from dbo.BulkOpsLog #19 (insert, 1 job(s)). | 4 | 0 | 4 | 0%
Load | 170_npc_giftcommitmentschedule_from_rd_load.sql | After: Campaign, GiftCommitment; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Issue |  | Jim Ziller | 2026-07-17 20:56 | 2026-07-17 20:56 |  |  | Auto-synced from dbo.BulkOpsLog #21 (insert, 1 job(s)). | 4 | 3 | 1 | 75%
Load | 420_giftdefaultdesignation_load.sql | After: Campaign, GiftCommitment, GiftDesignation; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-19 22:01 | 2026-07-19 22:01 |  |  | Auto-synced from dbo.BulkOpsLog #75 (insert, 1 job(s)). | 15 | 15 | 0 | 100%
Load | 400_giftrefund_load.sql | After: GiftTransaction; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-19 21:47 | 2026-07-19 21:47 |  |  | Auto-synced from dbo.BulkOpsLog #72 (insert, 1 job(s)). | 3 | 3 | 0 | 100%
Load | 410_giftsoftcredit_load.sql | After: Account, GiftTransaction; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftTransaction, GiftTransactionDesignation, PartyRelationshipGroup | Issue |  | Jim Ziller | 2026-07-19 21:48 | 2026-07-19 21:49 |  |  | Auto-synced from dbo.BulkOpsLog #73 (insert, 1 job(s)). | 23 | 0 | 23 | 0%
Load | 200_npc_gifttransaction_from_opportunity_load.sql | After: Account, Campaign, GiftCommitment, GiftCommitmentSchedule; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransactionDesignation, PartyRelationshipGroup | Issue |  | Jim Ziller | 2026-07-17 21:13 | 2026-07-17 21:14 |  |  | Auto-synced from dbo.BulkOpsLog #26 (insert, 1 job(s)). | 4 | 0 | 4 | 0%
Load | 220_npc_gifttransactiondesignation_from_allocation_load.sql | After: GiftDesignation, GiftTransaction; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, PartyRelationshipGroup | Issue |  | Jim Ziller | 2026-07-17 21:16 | 2026-07-17 21:17 |  |  | Auto-synced from dbo.BulkOpsLog #29 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
Load | 120_npc_partyrelationshipgroup_load.sql | After: Account; parallel with: Account, AccountContactRelation, CampaignMember, Contact, ContactContactRelation, ContactPointAddress, ContactPointEmail, ContactPointPhone, GiftCommitment, GiftCommitmentSchedule, GiftDefaultDesignation, GiftRefund, GiftSoftCredit, GiftTransaction, GiftTransactionDesignation | Issue |  | Jim Ziller | 2026-07-17 20:29 | 2026-07-17 20:29 |  |  | Auto-synced from dbo.BulkOpsLog #14 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
| 240_snowfake_contact_load.sql |  | Issue |  | Jim Ziller | 2026-07-17 16:02 | 2026-07-17 16:02 |  |  | Auto-synced from dbo.BulkOpsLog #2 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
| 240_snowfake_contact_load.sql |  | Issue |  | Jim Ziller | 2026-07-17 16:04 | 2026-07-17 16:05 |  |  | Auto-synced from dbo.BulkOpsLog #3 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
| 240_snowfake_contact_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 16:33 | 2026-07-17 16:34 |  |  | Auto-synced from dbo.BulkOpsLog #4 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| npsp__General_Accounting_Unit__c |  | Completed |  | Jim Ziller | 2026-07-17 16:36 | 2026-07-17 16:36 |  |  | Auto-synced from dbo.BulkOpsLog #5 (insert, 1 job(s)). | 2 | 0 | 0 | 0%
| npe03__Recurring_Donation__c |  | Completed |  | Jim Ziller | 2026-07-17 16:41 | 2026-07-17 16:42 |  |  | Auto-synced from dbo.BulkOpsLog #7 (insert, 1 job(s)). | 4 | 0 | 0 | 0%
| 070_opportunity_load_postgres.sql |  | Completed |  | Jim Ziller | 2026-07-17 16:47 | 2026-07-17 16:47 |  |  | Auto-synced from dbo.BulkOpsLog #8 (insert, 1 job(s)). | 6 | 0 | 0 | 0%
| npe01__OppPayment__c |  | Completed |  | Jim Ziller | 2026-07-17 16:48 | 2026-07-17 16:48 |  |  | Auto-synced from dbo.BulkOpsLog #9 (insert, 1 job(s)). | 5 | 0 | 0 | 0%
| npsp__Allocation__c |  | Completed |  | Jim Ziller | 2026-07-17 16:49 | 2026-07-17 16:50 |  |  | Auto-synced from dbo.BulkOpsLog #10 (insert, 1 job(s)). | 4 | 0 | 0 | 0%
| 100_npc_person_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:26 | 2026-07-17 20:26 |  |  | Auto-synced from dbo.BulkOpsLog #12 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 120_npc_partyrelationshipgroup_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:32 | 2026-07-17 20:32 |  |  | Auto-synced from dbo.BulkOpsLog #16 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 140_npc_campaignmember_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:44 | 2026-07-17 20:44 |  |  | Auto-synced from dbo.BulkOpsLog #17 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
| 160_npc_giftcommitment_from_rd_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:55 | 2026-07-17 20:55 |  |  | Auto-synced from dbo.BulkOpsLog #20 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
| 160_npc_giftcommitment_from_rd_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:57 | 2026-07-17 20:57 |  |  | Auto-synced from dbo.BulkOpsLog #22 (upsert, 1 job(s)). | 4 | 4 | 0 | 100%
| 170_npc_giftcommitmentschedule_from_rd_load.sql |  | Issue |  | Jim Ziller | 2026-07-17 20:58 | 2026-07-17 20:58 |  |  | Auto-synced from dbo.BulkOpsLog #23 (insert, 1 job(s)). | 4 | 1 | 3 | 25%
| 180_npc_giftcommitment_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:12 | 2026-07-17 21:12 |  |  | Auto-synced from dbo.BulkOpsLog #24 (insert, 1 job(s)). | 2 | 2 | 0 | 100%
| 190_npc_giftcommitmentschedule_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:12 | 2026-07-17 21:12 |  |  | Auto-synced from dbo.BulkOpsLog #25 (insert, 1 job(s)). | 2 | 2 | 0 | 100%
| 200_npc_gifttransaction_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:14 | 2026-07-17 21:14 |  |  | Auto-synced from dbo.BulkOpsLog #27 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
| 210_npc_gifttransaction_from_payment_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:15 | 2026-07-17 21:15 |  |  | Auto-synced from dbo.BulkOpsLog #28 (insert, 1 job(s)). | 5 | 5 | 0 | 100%
| 220_npc_gifttransactiondesignation_from_allocation_load.sql |  | Issue |  | Jim Ziller | 2026-07-17 21:17 | 2026-07-17 21:17 |  |  | Auto-synced from dbo.BulkOpsLog #30 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
| 220_npc_gifttransactiondesignation_from_allocation_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:18 | 2026-07-17 21:18 |  |  | Auto-synced from dbo.BulkOpsLog #31 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 250_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:42 | 2026-07-18 18:43 |  |  | Auto-synced from dbo.BulkOpsLog #32 (delete, 1 job(s)). | 8 | 8 | 0 | 100%
| 260_partyrelationshipgroup_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:43 | 2026-07-18 18:43 |  |  | Auto-synced from dbo.BulkOpsLog #33 (delete, 1 job(s)). | 8 | 8 | 0 | 100%
| 390_snowfake_gifttransaction_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:44 | 2026-07-18 18:44 |  |  | Auto-synced from dbo.BulkOpsLog #34 (delete, 1 job(s)). | 4 | 4 | 0 | 100%
| 110_npc_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:47 | 2026-07-18 18:47 |  |  | Auto-synced from dbo.BulkOpsLog #35 (insert, 1 job(s)). | 8 | 0 | 0 | 0%
| 120_npc_partyrelationshipgroup_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:50 | 2026-07-18 18:50 |  |  | Auto-synced from dbo.BulkOpsLog #36 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 200_npc_gifttransaction_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:50 | 2026-07-18 18:50 |  |  | Auto-synced from dbo.BulkOpsLog #37 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
| 090_npc_household_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 13:15 | 2026-07-19 13:16 |  |  | Auto-synced from dbo.BulkOpsLog #38 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 020_contact_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 13:17 | 2026-07-19 13:17 |  |  | Auto-synced from dbo.BulkOpsLog #39 (insert, 1 job(s)). | 16 | 16 | 0 | 100%
| 110_npc_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 13:37 | 2026-07-19 13:37 |  |  | Auto-synced from dbo.BulkOpsLog #40 (insert, 1 job(s)). | 16 | 0 | 0 | 0%
| 110_npc_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 14:10 | 2026-07-19 14:10 |  |  | Auto-synced from dbo.BulkOpsLog #41 (update, 1 job(s)). | 16 | 0 | 0 | 0%
| 120_npc_partyrelationshipgroup_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 14:11 | 2026-07-19 14:11 |  |  | Auto-synced from dbo.BulkOpsLog #42 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 280_snowfake_organization_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 14:14 | 2026-07-19 14:14 |  |  | Auto-synced from dbo.BulkOpsLog #44 (insert, 1 job(s)). | 5 | 5 | 0 | 100%
| 250_accountcontactrelation_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 14:55 | 2026-07-19 14:55 |  |  | Auto-synced from dbo.BulkOpsLog #45 (update, 1 job(s)). | 16 | 0 | 16 | 0%
| 110_npc_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 14:57 | 2026-07-19 14:57 |  |  | Auto-synced from dbo.BulkOpsLog #46 (update, 1 job(s)). | 16 | 16 | 0 | 100%
| 250_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 15:21 | 2026-07-19 15:21 |  |  | Auto-synced from dbo.BulkOpsLog #47 (update, 1 job(s)). | 16 | 16 | 0 | 100%
| 250_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 15:32 | 2026-07-19 15:32 |  |  | Auto-synced from dbo.BulkOpsLog #48 (update, 1 job(s)). | 16 | 16 | 0 | 100%
| 100_npc_person_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 15:37 | 2026-07-19 15:37 |  |  | Auto-synced from dbo.BulkOpsLog #49 (insert, 1 job(s)). | 10 | 10 | 0 | 100%
| 300_contactpointaddress_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 15:51 | 2026-07-19 15:52 |  |  | Auto-synced from dbo.BulkOpsLog #51 (upsert, 1 job(s)). | 35 | 35 | 0 | 100%
| 130_npc_campaign_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 18:32 | 2026-07-19 18:33 |  |  | Auto-synced from dbo.BulkOpsLog #54 (insert, 1 job(s)). | 4 | 3 | 1 | 75%
| 130_npc_campaign_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 18:33 | 2026-07-19 18:33 |  |  | Auto-synced from dbo.BulkOpsLog #55 (upsert, 1 job(s)). | 4 | 4 | 0 | 100%
| 140_npc_campaignmember_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 18:58 | 2026-07-19 18:58 |  |  | Auto-synced from dbo.BulkOpsLog #56 (insert, 1 job(s)). | 19 | 19 | 0 | 100%
| 150_npc_giftdesignation_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 19:15 | 2026-07-19 19:16 |  |  | Auto-synced from dbo.BulkOpsLog #57 (insert, 1 job(s)). | 6 | 5 | 1 | 83.33%
| 150_npc_giftdesignation_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 19:16 | 2026-07-19 19:16 |  |  | Auto-synced from dbo.BulkOpsLog #58 (upsert, 1 job(s)). | 6 | 6 | 0 | 100%
| 360_snowfake_giftcommitment_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 19:19 | 2026-07-19 19:19 |  |  | Auto-synced from dbo.BulkOpsLog #59 (insert, 1 job(s)). | 15 | 15 | 0 | 100%
| 170_npc_giftcommitmentschedule_from_rd_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 19:20 | 2026-07-19 19:20 |  |  | Auto-synced from dbo.BulkOpsLog #60 (insert, 1 job(s)). | 3 | 3 | 0 | 100%
| 360_snowfake_giftcommitment_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 20:06 | 2026-07-19 20:07 |  |  | Auto-synced from dbo.BulkOpsLog #61 (update, 1 job(s)). | 3 | 3 | 0 | 100%
| 360_snowfake_giftcommitment_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 20:12 | 2026-07-19 20:12 |  |  | Auto-synced from dbo.BulkOpsLog #62 (delete, 1 job(s)). | 12 | 12 | 0 | 100%
| 360_snowfake_giftcommitment_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 20:19 | 2026-07-19 20:19 |  |  | Auto-synced from dbo.BulkOpsLog #63 (upsert, 1 job(s)). | 15 | 15 | 0 | 100%
| 170_npc_giftcommitmentschedule_from_rd_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 20:28 | 2026-07-19 20:29 |  |  | Auto-synced from dbo.BulkOpsLog #64 (insert, 1 job(s)). | 12 | 12 | 0 | 100%
| 390_snowfake_gifttransaction_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 21:33 | 2026-07-19 21:33 |  |  | Auto-synced from dbo.BulkOpsLog #65 (insert, 1 job(s)). | 40 | 16 | 24 | 40%
| 390_snowfake_gifttransaction_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 21:34 | 2026-07-19 21:34 |  |  | Auto-synced from dbo.BulkOpsLog #66 (upsert, 1 job(s)). | 40 | 31 | 9 | 77.5%
| 390_snowfake_gifttransaction_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 21:35 | 2026-07-19 21:35 |  |  | Auto-synced from dbo.BulkOpsLog #67 (upsert, 1 job(s)). | 40 | 38 | 2 | 95%
| 390_snowfake_gifttransaction_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 21:36 | 2026-07-19 21:36 |  |  | Auto-synced from dbo.BulkOpsLog #68 (upsert, 1 job(s)). | 40 | 38 | 2 | 95%
| 390_snowfake_gifttransaction_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 21:40 | 2026-07-19 21:40 |  |  | Auto-synced from dbo.BulkOpsLog #69 (upsert, 1 job(s)). | 40 | 38 | 2 | 95%
| 390_snowfake_gifttransaction_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 21:41 | 2026-07-19 21:41 |  |  | Auto-synced from dbo.BulkOpsLog #70 (delete, 1 job(s)). | 2 | 2 | 0 | 100%
| 390_snowfake_gifttransaction_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 21:42 | 2026-07-19 21:42 |  |  | Auto-synced from dbo.BulkOpsLog #71 (upsert, 1 job(s)). | 40 | 40 | 0 | 100%
| 410_giftsoftcredit_load.sql |  | Completed |  | Jim Ziller | 2026-07-19 21:53 | 2026-07-19 21:53 |  |  | Auto-synced from dbo.BulkOpsLog #74 (insert, 1 job(s)). | 23 | 23 | 0 | 100%
| 220_npc_gifttransactiondesignation_from_allocation_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 22:02 | 2026-07-19 22:02 |  |  | Auto-synced from dbo.BulkOpsLog #76 (insert, 1 job(s)). | 60 | 59 | 1 | 98.33%
| 430_gifttransactiondesignation_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 22:04 | 2026-07-19 22:05 |  |  | Auto-synced from dbo.BulkOpsLog #77 (insert, 1 job(s)). | 1 | 0 | 1 | 0%
| 430_gifttransactiondesignation_load.sql |  | Issue |  | Jim Ziller | 2026-07-19 22:07 | 2026-07-19 22:07 |  |  | Auto-synced from dbo.BulkOpsLog #78 (update, 1 job(s)). | 1 | 0 | 1 | 0%
| 430_gifttransactiondesignation_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:15 | 2026-07-20 18:15 |  |  | Auto-synced from dbo.BulkOpsLog #79 (delete, 1 job(s)). | 65 | 65 | 0 | 100%
| 420_giftdefaultdesignation_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:15 | 2026-07-20 18:15 |  |  | Auto-synced from dbo.BulkOpsLog #80 (delete, 1 job(s)). | 15 | 15 | 0 | 100%
| 410_giftsoftcredit_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:15 | 2026-07-20 18:16 |  |  | Auto-synced from dbo.BulkOpsLog #81 (delete, 1 job(s)). | 23 | 23 | 0 | 100%
| 400_giftrefund_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:16 | 2026-07-20 18:16 |  |  | Auto-synced from dbo.BulkOpsLog #82 (delete, 1 job(s)). | 3 | 3 | 0 | 100%
| 390_snowfake_gifttransaction_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:17 | 2026-07-20 18:17 |  |  | Auto-synced from dbo.BulkOpsLog #83 (delete, 1 job(s)). | 49 | 49 | 0 | 100%
| 370_giftcommitmentschedule_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:17 | 2026-07-20 18:17 |  |  | Auto-synced from dbo.BulkOpsLog #84 (delete, 1 job(s)). | 21 | 21 | 0 | 100%
| 360_snowfake_giftcommitment_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:18 | 2026-07-20 18:18 |  |  | Auto-synced from dbo.BulkOpsLog #85 (delete, 1 job(s)). | 21 | 21 | 0 | 100%
| 350_snowfake_giftdesignation_load.sql |  | Issue |  | Jim Ziller | 2026-07-20 18:18 | 2026-07-20 18:18 |  |  | Auto-synced from dbo.BulkOpsLog #86 (delete, 1 job(s)). | 8 | 2 | 6 | 25%
| 340_campaignmember_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:19 | 2026-07-20 18:19 |  |  | Auto-synced from dbo.BulkOpsLog #87 (delete, 1 job(s)). | 23 | 23 | 0 | 100%
| 330_snowfake_campaign_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:19 | 2026-07-20 18:19 |  |  | Auto-synced from dbo.BulkOpsLog #88 (delete, 1 job(s)). | 6 | 6 | 0 | 100%
| 350_snowfake_giftdesignation_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:20 | 2026-07-20 18:20 |  |  | Auto-synced from dbo.BulkOpsLog #89 (update, 1 job(s)). | 6 | 6 | 0 | 100%
| 350_snowfake_giftdesignation_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:21 | 2026-07-20 18:21 |  |  | Auto-synced from dbo.BulkOpsLog #90 (delete, 1 job(s)). | 6 | 6 | 0 | 100%
| 320_contactpointemail_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:22 | 2026-07-20 18:22 |  |  | Auto-synced from dbo.BulkOpsLog #91 (delete, 1 job(s)). | 35 | 35 | 0 | 100%
| 310_contactpointphone_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:22 | 2026-07-20 18:22 |  |  | Auto-synced from dbo.BulkOpsLog #92 (delete, 1 job(s)). | 35 | 35 | 0 | 100%
| 300_contactpointaddress_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:22 | 2026-07-20 18:23 |  |  | Auto-synced from dbo.BulkOpsLog #93 (delete, 1 job(s)). | 35 | 35 | 0 | 100%
| 270_contactcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:23 | 2026-07-20 18:23 |  |  | Auto-synced from dbo.BulkOpsLog #94 (delete, 1 job(s)). | 5 | 5 | 0 | 100%
| 250_accountcontactrelation_load.sql |  | Issue |  | Jim Ziller | 2026-07-20 18:24 | 2026-07-20 18:24 |  |  | Auto-synced from dbo.BulkOpsLog #95 (delete, 1 job(s)). | 24 | 8 | 16 | 33.33%
| 250_accountcontactrelation_load.sql |  | Issue |  | Jim Ziller | 2026-07-20 18:24 | 2026-07-20 18:24 |  |  | Auto-synced from dbo.BulkOpsLog #96 (delete, 1 job(s)). | 16 | 0 | 16 | 0%
| 260_partyrelationshipgroup_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:27 | 2026-07-20 18:27 |  |  | Auto-synced from dbo.BulkOpsLog #97 (delete, 1 job(s)). | 16 | 16 | 0 | 100%
| 240_snowfake_contact_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 18:27 | 2026-07-20 18:27 |  |  | Auto-synced from dbo.BulkOpsLog #98 (delete, 1 job(s)). | 16 | 16 | 0 | 100%
| 290_snowfake_person_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-20 23:19 | 2026-07-20 23:19 |  |  | Auto-synced from dbo.BulkOpsLog #99 (delete, 1 job(s)). | 39 | 39 | 0 | 100%
| 090_npc_household_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 15:57 | 2026-07-21 15:58 |  |  | Auto-synced from dbo.BulkOpsLog #100 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 020_contact_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 15:59 | 2026-07-21 15:59 |  |  | Auto-synced from dbo.BulkOpsLog #101 (insert, 1 job(s)). | 19 | 19 | 0 | 100%
| 110_npc_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:00 | 2026-07-21 16:00 |  |  | Auto-synced from dbo.BulkOpsLog #102 (update, 1 job(s)). | 19 | 19 | 0 | 100%
| 120_npc_partyrelationshipgroup_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:02 | 2026-07-21 16:02 |  |  | Auto-synced from dbo.BulkOpsLog #103 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 270_contactcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:05 | 2026-07-21 16:05 |  |  | Auto-synced from dbo.BulkOpsLog #104 (insert, 1 job(s)). | 7 | 7 | 0 | 100%
| 280_snowfake_organization_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:06 | 2026-07-21 16:06 |  |  | Auto-synced from dbo.BulkOpsLog #105 (insert, 1 job(s)). | 5 | 5 | 0 | 100%
| 100_npc_person_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:10 | 2026-07-21 16:11 |  |  | Auto-synced from dbo.BulkOpsLog #106 (insert, 1 job(s)). | 10 | 10 | 0 | 100%
| 300_contactpointaddress_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:31 | 2026-07-21 16:31 |  |  | Auto-synced from dbo.BulkOpsLog #107 (insert, 1 job(s)). | 35 | 35 | 0 | 100%
| 310_contactpointphone_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:43 | 2026-07-21 16:43 |  |  | Auto-synced from dbo.BulkOpsLog #108 (insert, 1 job(s)). | 35 | 35 | 0 | 100%
| 320_contactpointemail_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:43 | 2026-07-21 16:44 |  |  | Auto-synced from dbo.BulkOpsLog #109 (insert, 1 job(s)). | 35 | 35 | 0 | 100%
| 130_npc_campaign_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:49 | 2026-07-21 16:49 |  |  | Auto-synced from dbo.BulkOpsLog #110 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
| 140_npc_campaignmember_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 16:50 | 2026-07-21 16:50 |  |  | Auto-synced from dbo.BulkOpsLog #111 (insert, 1 job(s)). | 21 | 21 | 0 | 100%
| 150_npc_giftdesignation_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 17:05 | 2026-07-21 17:05 |  |  | Auto-synced from dbo.BulkOpsLog #112 (insert, 1 job(s)). | 6 | 6 | 0 | 100%
| 360_snowfake_giftcommitment_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 17:39 | 2026-07-21 17:39 |  |  | Auto-synced from dbo.BulkOpsLog #113 (insert, 1 job(s)). | 15 | 15 | 0 | 100%
| 170_npc_giftcommitmentschedule_from_rd_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 20:51 | 2026-07-21 20:51 |  |  | Auto-synced from dbo.BulkOpsLog #114 (insert, 1 job(s)). | 3 | 3 | 0 | 100%
| 390_snowfake_gifttransaction_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 21:31 | 2026-07-21 21:31 |  |  | Auto-synced from dbo.BulkOpsLog #115 (insert, 1 job(s)). | 40 | 40 | 0 | 100%
| 400_giftrefund_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 21:32 | 2026-07-21 21:32 |  |  | Auto-synced from dbo.BulkOpsLog #116 (insert, 1 job(s)). | 2 | 2 | 0 | 100%
| 410_giftsoftcredit_load.sql |  | Completed |  | Jim Ziller | 2026-07-21 21:36 | 2026-07-21 21:37 |  |  | Auto-synced from dbo.BulkOpsLog #117 (insert, 1 job(s)). | 16 | 16 | 0 | 100%
| 420_giftdefaultdesignation_load.sql |  | Issue |  | Jim Ziller | 2026-07-21 21:38 | 2026-07-21 21:38 |  |  | Auto-synced from dbo.BulkOpsLog #118 (insert, 1 job(s)). | 15 | 0 | 15 | 0%
| 110_npc_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-22 00:04 | 2026-07-22 00:04 |  |  | Auto-synced from dbo.BulkOpsLog #119 (update, 1 job(s)). | 19 | 19 | 0 | 100%
| 220_npc_gifttransactiondesignation_from_allocation_load.sql |  | Issue |  | Jim Ziller | 2026-07-22 00:36 | 2026-07-22 00:37 |  |  | Auto-synced from dbo.BulkOpsLog #120 (insert, 1 job(s)). | 60 | 59 | 1 | 98.33%
Post-Migration Steps
Salesforce Config Changes | Re-enable Email Deliverability to its normal setting | None | Not Started | Yes
Salesforce Config Changes | Re-enable CPQ/Billing automation (or other managed-package automation) | None | Not Started | Yes
Salesforce Config Changes | Re-enable outbound automation disabled during Pre-Migration | None | Not Started | Yes
Post Migration | Spot-check row counts against source | None | Not Started | No
Post Migration | Notify stakeholders the load is complete | None | Not Started | No