## Dev1
Project | Example Migration Project
Source Environment | SQL Server: SF_Migration
Target Environment | TARGET_ORG_ALIAS
Git Repository | https://github.com/jpziller/DataMigration
Commit / Branch | 61ab8472 (main)
Scripts (as of this commit) | https://github.com/jpziller/DataMigration/tree/61ab84729dc91dfad8eb2b1c9aed5492539dc1d7/sql/transformations
JIRA Project
Last Synced Log Id | 5
Stage | Object | Dependency | Status | Critical | Person Responsible | Begin Time | End Time | Execution Time | JIRA Ticket Link | Notes | Total Records | Success Records | Failed Records | Success Percent | Error Details
Pre-Migration Steps
Salesforce Config Changes | Confirm Email Deliverability setting (Setup > Email Administration > Deliverability) | None | Not Started | Yes
Salesforce Config Changes | Disable CPQ/Billing automation (or other managed-package automation) on target objects | None | Not Started | Yes
Salesforce Config Changes | Disable outbound automation that could email real contacts (workflow/Flow email alerts, approval processes) | None | Not Started | Yes
Pre Migration | Confirm target org/alias and auth mode for this pass | None | Not Started | Yes
Pre Migration | Run analyze-org-risk against in-scope objects | None | Not Started | No
Pre Migration | Take a backup/export of any target data being overwritten | None | Not Started | No
Source Download and Load Steps
Load Steps
Load | 010_account_load.sql | None | Completed |  | Demo User | 2026-07-11T17:38:27.638139 | 2026-07-11T17:38:36.492095 |  |  | Auto-synced from dbo.BulkOpsLog #1 (insert, 1 job(s)). | 300 | 300 | 0 | 100%
Load | 020_contact_load.sql | After: Account | Completed |  | Demo User | 2026-07-11T19:35:30.873591 | 2026-07-11T19:35:45.181006 |  |  | Auto-synced from dbo.BulkOpsLog #2 (insert, 1 job(s)). | 446 | 446 | 0 | 100%
| 030_opportunity_load.sql |  | Completed |  | Demo User | 2026-07-11T19:36:25.900677 | 2026-07-11T19:36:54.189318 |  |  | Auto-synced from dbo.BulkOpsLog #3 (insert, 2 job(s)). | 230 | 230 | 0 | 100%
| 040_task_load.sql |  | Issue |  | Demo User | 2026-07-11T19:37:56.291523 | 2026-07-11T19:38:12.764338 |  |  | Auto-synced from dbo.BulkOpsLog #4 (insert, 2 job(s)). | 530 | 0 | 530 | 0%
| 040_task_load.sql |  | Completed |  | Demo User | 2026-07-11T19:41:24.302042 | 2026-07-11T19:41:45.538388 |  |  | Auto-synced from dbo.BulkOpsLog #5 (insert, 2 job(s)). | 530 | 530 | 0 | 100%
Post-Migration Steps
Salesforce Config Changes | Re-enable Email Deliverability to its normal setting | None | Not Started | Yes
Salesforce Config Changes | Re-enable CPQ/Billing automation (or other managed-package automation) | None | Not Started | Yes
Salesforce Config Changes | Re-enable outbound automation disabled during Pre-Migration | None | Not Started | Yes
Post Migration | Spot-check row counts against source | None | Not Started | No
Post Migration | Notify stakeholders the load is complete | None | Not Started | No

## Sample1
Project | Full Pipeline Sample Run
Source Environment
Target Environment | D360_PLAYGROUND
Git Repository | https://github.com/jpziller/DataMigration
Commit / Branch | ddd8a47b (main)
Scripts (as of this commit) | https://github.com/jpziller/DataMigration/tree/ddd8a47b7eeac26704d489c233a39b28a87efbfc/sql/transformations
JIRA Project
Last Synced Log Id
Last Synced Source Ingestion Log Id
Stage | Object | Dependency | Status | Critical | Person Responsible | Begin Time | End Time | Execution Time | JIRA Ticket Link | Notes | Total Records | Success Records | Failed Records | Success Percent | Error Details
Pre-Migration Steps
Salesforce Config Changes | Confirm Email Deliverability setting (Setup > Email Administration > Deliverability) | None | Not Started | Yes
Salesforce Config Changes | Disable CPQ/Billing automation (or other managed-package automation) on target objects | None | Not Started | Yes
Salesforce Config Changes | Disable outbound automation that could email real contacts (workflow/Flow email alerts, approval processes) | None | Not Started | Yes
Pre Migration | Confirm target org/alias and auth mode for this pass | None | Not Started | Yes
Pre Migration | Run analyze-org-risk against in-scope objects | None | Not Started | No
Pre Migration | Take a backup/export of any target data being overwritten | None | Not Started | No
Source Download and Load Steps
Load Steps
Load | 010_account_load.sql | None | Completed |  | Jim Ziller | 2026-07-13 11:30 | 2026-07-13 11:30 |  |  | Live insert into D360_PLAYGROUND (sample/practice run) | 5 | 5 | 0 | 100
Load | 020_contact_load.sql | After: Account | Completed |  | Jim Ziller | 2026-07-13 11:30 | 2026-07-13 11:30 |  |  | Live insert into D360_PLAYGROUND (sample/practice run) | 8 | 8 | 0 | 100
Load | 030_opportunity_load.sql | After: Account, Contact | Completed |  | Jim Ziller | 2026-07-13 11:30 | 2026-07-13 11:30 |  |  | Live insert into D360_PLAYGROUND (sample/practice run) | 13 | 13 | 0 | 100
Load | 040_task_load.sql | After: Account, Contact, Opportunity | Completed |  | Jim Ziller | 2026-07-13 11:30 | 2026-07-13 11:30 |  |  | Live insert into D360_PLAYGROUND (sample/practice run) | 27 | 27 | 0 | 100
Post-Migration Steps
Salesforce Config Changes | Re-enable Email Deliverability to its normal setting | None | Not Started | Yes
Salesforce Config Changes | Re-enable CPQ/Billing automation (or other managed-package automation) | None | Not Started | Yes
Salesforce Config Changes | Re-enable outbound automation disabled during Pre-Migration | None | Not Started | Yes
Post Migration | Spot-check row counts against source | None | Not Started | No
Post Migration | Notify stakeholders the load is complete | None | Not Started | No

## Postgres1
Project | Full Pipeline Sample Run
Source Environment
Target Environment | D360_PLAYGROUND
Git Repository | https://github.com/jpziller/DataMigration
Commit / Branch
Scripts (as of this commit) | https://github.com/jpziller/DataMigration/tree/ddd8a47b7eeac26704d489c233a39b28a87efbfc/sql/transformations
JIRA Project
Last Synced Log Id
Last Synced Source Ingestion Log Id
Stage | Object | Dependency | Status | Critical | Person Responsible | Begin Time | End Time | Execution Time | JIRA Ticket Link | Notes | Total Records | Success Records | Failed Records | Success Percent | Error Details
Pre-Migration Steps
Salesforce Config Changes | Confirm Email Deliverability setting (Setup > Email Administration > Deliverability) | None | Not Started | Yes
Salesforce Config Changes | Disable CPQ/Billing automation (or other managed-package automation) on target objects | None | Not Started | Yes
Salesforce Config Changes | Disable outbound automation that could email real contacts (workflow/Flow email alerts, approval processes) | None | Not Started | Yes
Pre Migration | Confirm target org/alias and auth mode for this pass | None | Not Started | Yes
Pre Migration | Run analyze-org-risk against in-scope objects | None | Not Started | No
Pre Migration | Take a backup/export of any target data being overwritten | None | Not Started | No
Source Download and Load Steps
Load Steps
Load | 010_account_load.sql | None | Not Started
Load | 020_contact_load.sql | After: Account | Not Started
Load | 030_opportunity_load.sql | After: Account, Contact | Not Started
Load | 040_task_load.sql | After: Account, Contact, Opportunity | Not Started
Post-Migration Steps
Salesforce Config Changes | Re-enable Email Deliverability to its normal setting | None | Not Started | Yes
Salesforce Config Changes | Re-enable CPQ/Billing automation (or other managed-package automation) | None | Not Started | Yes
Salesforce Config Changes | Re-enable outbound automation disabled during Pre-Migration | None | Not Started | Yes
Post Migration | Spot-check row counts against source | None | Not Started | No
Post Migration | Notify stakeholders the load is complete | None | Not Started | No

## NPSP_to_NPC_PoC
Project | NPSP-to-NPC Migration Proof-of-Concept
Source Environment | NPSP_SOURCE
Target Environment | NPC_TARGET_v2
Git Repository | https://github.com/jpziller/DataMigration
Commit / Branch | ececcbb6 (feature/npsp-to-npc-migration-poc)
Scripts (as of this commit) | https://github.com/jpziller/DataMigration/tree/ececcbb6bb170384b3fc968fe82f37e62a34e51f/sql/transformations
JIRA Project
Last Synced Log Id | 37
Last Synced Source Ingestion Log Id
Stage | Object | Dependency | Status | Critical | Person Responsible | Begin Time | End Time | Execution Time | JIRA Ticket Link | Notes | Total Records | Success Records | Failed Records | Success Percent | Error Details
Pre-Migration Steps
Salesforce Config Changes | Confirm Email Deliverability setting (Setup > Email Administration > Deliverability) | None | Not Started | Yes
Salesforce Config Changes | Disable CPQ/Billing automation (or other managed-package automation) on target objects | None | Not Started | Yes
Salesforce Config Changes | Disable outbound automation that could email real contacts (workflow/Flow email alerts, approval processes) | None | Not Started | Yes
Pre Migration | Confirm target org/alias and auth mode for this pass | None | Not Started | Yes
Pre Migration | Run analyze-org-risk against in-scope objects | None | Not Started | No
Pre Migration | Take a backup/export of any target data being overwritten | None | Not Started | No
Source Download and Load Steps
Load Steps
Load | 100_npc_person_account_load.sql | None; parallel with: Campaign, GiftDesignation | Completed |  | Jim Ziller | 2026-07-17 20:26 | 2026-07-17 20:26 |  |  | Auto-synced from dbo.BulkOpsLog #11 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
Load | 130_npc_campaign_load.sql | None; parallel with: Account, GiftDesignation | Completed |  | Jim Ziller | 2026-07-17 20:29 | 2026-07-17 20:29 |  |  | Auto-synced from dbo.BulkOpsLog #15 (insert, 1 job(s)). | 2 | 0 | 0 | 0%
Load | GiftDesignation | None; parallel with: Account, Campaign | Completed |  | Jim Ziller | 2026-07-17 20:45 | 2026-07-17 20:46 |  |  | Auto-synced from dbo.BulkOpsLog #18 (insert, 1 job(s)). | 2 | 0 | 0 | 0%
Load | 110_npc_accountcontactrelation_load.sql | After: Account; parallel with: CampaignMember, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-17 20:28 | 2026-07-17 20:29 |  |  | Auto-synced from dbo.BulkOpsLog #13 (insert, 1 job(s)). | 8 | 0 | 0 | 0%
Load | 140_npc_campaignmember_load.sql | After: Account, Campaign; parallel with: AccountContactRelation, PartyRelationshipGroup | Completed |  | Jim Ziller | 2026-07-17 16:40 | 2026-07-17 16:40 |  |  | Auto-synced from dbo.BulkOpsLog #6 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
Load | PartyRelationshipGroup | After: Account; parallel with: AccountContactRelation, CampaignMember | Issue |  | Jim Ziller | 2026-07-17 20:29 | 2026-07-17 20:29 |  |  | Auto-synced from dbo.BulkOpsLog #14 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
Load | 200_npc_gifttransaction_from_opportunity_load.sql | After: Account, Campaign, GiftCommitmentSchedule; parallel with: GiftCommitmentSchedule, GiftTransaction, GiftTransactionDesignation | Completed |  | Jim Ziller | 2026-07-17 16:47 | 2026-07-17 16:47 |  |  | Auto-synced from dbo.BulkOpsLog #8 (insert, 1 job(s)). | 6 | 0 | 0 | 0%
Load | 190_npc_giftcommitmentschedule_from_opportunity_load.sql | After: Campaign, GiftCommitment; parallel with: GiftCommitment, GiftTransaction, GiftTransactionDesignation | Issue |  | Jim Ziller | 2026-07-17 20:56 | 2026-07-17 20:56 |  |  | Auto-synced from dbo.BulkOpsLog #21 (insert, 1 job(s)). | 4 | 3 | 1 | 75%
Load | 210_npc_gifttransaction_from_payment_load.sql | After: Account, Campaign, GiftCommitment, GiftCommitmentSchedule; parallel with: GiftCommitment, GiftCommitmentSchedule, GiftTransactionDesignation | Issue |  | Jim Ziller | 2026-07-17 21:13 | 2026-07-17 21:14 |  |  | Auto-synced from dbo.BulkOpsLog #26 (insert, 1 job(s)). | 4 | 0 | 4 | 0%
Load | 220_npc_gifttransactiondesignation_from_allocation_load.sql | After: GiftDesignation, GiftTransaction; parallel with: GiftCommitment, GiftCommitmentSchedule, GiftTransaction | Issue |  | Jim Ziller | 2026-07-17 21:16 | 2026-07-17 21:17 |  |  | Auto-synced from dbo.BulkOpsLog #29 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
| 060_contact_load_postgres.sql |  | Completed |  | Jim Ziller | 2026-07-14 18:55 | 2026-07-14 18:55 |  |  | Auto-synced from dbo.BulkOpsLog #1 (upsert, 1 job(s)). | 8 | 8 | 0 | 100%
| 060_contact_load_postgres.sql |  | Issue |  | Jim Ziller | 2026-07-17 16:02 | 2026-07-17 16:02 |  |  | Auto-synced from dbo.BulkOpsLog #2 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
| 060_contact_load_postgres.sql |  | Issue |  | Jim Ziller | 2026-07-17 16:04 | 2026-07-17 16:05 |  |  | Auto-synced from dbo.BulkOpsLog #3 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
| 060_contact_load_postgres.sql |  | Completed |  | Jim Ziller | 2026-07-17 16:33 | 2026-07-17 16:34 |  |  | Auto-synced from dbo.BulkOpsLog #4 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| npsp__General_Accounting_Unit__c |  | Completed |  | Jim Ziller | 2026-07-17 16:36 | 2026-07-17 16:36 |  |  | Auto-synced from dbo.BulkOpsLog #5 (insert, 1 job(s)). | 2 | 0 | 0 | 0%
| npe03__Recurring_Donation__c |  | Completed |  | Jim Ziller | 2026-07-17 16:41 | 2026-07-17 16:42 |  |  | Auto-synced from dbo.BulkOpsLog #7 (insert, 1 job(s)). | 4 | 0 | 0 | 0%
| npe01__OppPayment__c |  | Completed |  | Jim Ziller | 2026-07-17 16:48 | 2026-07-17 16:48 |  |  | Auto-synced from dbo.BulkOpsLog #9 (insert, 1 job(s)). | 5 | 0 | 0 | 0%
| npsp__Allocation__c |  | Completed |  | Jim Ziller | 2026-07-17 16:49 | 2026-07-17 16:50 |  |  | Auto-synced from dbo.BulkOpsLog #10 (insert, 1 job(s)). | 4 | 0 | 0 | 0%
| 100_npc_person_account_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:26 | 2026-07-17 20:26 |  |  | Auto-synced from dbo.BulkOpsLog #12 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| PartyRelationshipGroup |  | Completed |  | Jim Ziller | 2026-07-17 20:32 | 2026-07-17 20:32 |  |  | Auto-synced from dbo.BulkOpsLog #16 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 140_npc_campaignmember_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:44 | 2026-07-17 20:44 |  |  | Auto-synced from dbo.BulkOpsLog #17 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
| 180_npc_giftcommitment_from_opportunity_load.sql |  | Issue |  | Jim Ziller | 2026-07-17 20:55 | 2026-07-17 20:55 |  |  | Auto-synced from dbo.BulkOpsLog #19 (insert, 1 job(s)). | 4 | 0 | 4 | 0%
| 180_npc_giftcommitment_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:55 | 2026-07-17 20:55 |  |  | Auto-synced from dbo.BulkOpsLog #20 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
| 180_npc_giftcommitment_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 20:57 | 2026-07-17 20:57 |  |  | Auto-synced from dbo.BulkOpsLog #22 (upsert, 1 job(s)). | 4 | 4 | 0 | 100%
| 190_npc_giftcommitmentschedule_from_opportunity_load.sql |  | Issue |  | Jim Ziller | 2026-07-17 20:58 | 2026-07-17 20:58 |  |  | Auto-synced from dbo.BulkOpsLog #23 (insert, 1 job(s)). | 4 | 1 | 3 | 25%
| 180_npc_giftcommitment_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:12 | 2026-07-17 21:12 |  |  | Auto-synced from dbo.BulkOpsLog #24 (insert, 1 job(s)). | 2 | 2 | 0 | 100%
| 190_npc_giftcommitmentschedule_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:12 | 2026-07-17 21:12 |  |  | Auto-synced from dbo.BulkOpsLog #25 (insert, 1 job(s)). | 2 | 2 | 0 | 100%
| 210_npc_gifttransaction_from_payment_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:14 | 2026-07-17 21:14 |  |  | Auto-synced from dbo.BulkOpsLog #27 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
| 210_npc_gifttransaction_from_payment_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:15 | 2026-07-17 21:15 |  |  | Auto-synced from dbo.BulkOpsLog #28 (insert, 1 job(s)). | 5 | 5 | 0 | 100%
| 220_npc_gifttransactiondesignation_from_allocation_load.sql |  | Issue |  | Jim Ziller | 2026-07-17 21:17 | 2026-07-17 21:17 |  |  | Auto-synced from dbo.BulkOpsLog #30 (insert, 1 job(s)). | 8 | 0 | 8 | 0%
| 220_npc_gifttransactiondesignation_from_allocation_load.sql |  | Completed |  | Jim Ziller | 2026-07-17 21:18 | 2026-07-17 21:18 |  |  | Auto-synced from dbo.BulkOpsLog #31 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 110_npc_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:42 | 2026-07-18 18:43 |  |  | Auto-synced from dbo.BulkOpsLog #32 (delete, 1 job(s)). | 8 | 8 | 0 | 100%
| 120_npc_partyrelationshipgroup_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:43 | 2026-07-18 18:43 |  |  | Auto-synced from dbo.BulkOpsLog #33 (delete, 1 job(s)). | 8 | 8 | 0 | 100%
| 210_npc_gifttransaction_from_payment_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:44 | 2026-07-18 18:44 |  |  | Auto-synced from dbo.BulkOpsLog #34 (delete, 1 job(s)). | 4 | 4 | 0 | 100%
| 110_npc_accountcontactrelation_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:47 | 2026-07-18 18:47 |  |  | Auto-synced from dbo.BulkOpsLog #35 (insert, 1 job(s)). | 8 | 0 | 0 | 0%
| 120_npc_partyrelationshipgroup_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:50 | 2026-07-18 18:50 |  |  | Auto-synced from dbo.BulkOpsLog #36 (insert, 1 job(s)). | 8 | 8 | 0 | 100%
| 200_npc_gifttransaction_from_opportunity_load.sql |  | Completed |  | Jim Ziller | 2026-07-18 18:50 | 2026-07-18 18:50 |  |  | Auto-synced from dbo.BulkOpsLog #37 (insert, 1 job(s)). | 4 | 4 | 0 | 100%
Post-Migration Steps
Salesforce Config Changes | Re-enable Email Deliverability to its normal setting | None | Not Started | Yes
Salesforce Config Changes | Re-enable CPQ/Billing automation (or other managed-package automation) | None | Not Started | Yes
Salesforce Config Changes | Re-enable outbound automation disabled during Pre-Migration | None | Not Started | Yes
Post Migration | Spot-check row counts against source | None | Not Started | No
Post Migration | Notify stakeholders the load is complete | None | Not Started | No

## NPC_Fundraising_Sample
Project
Source Environment | SQL Server: SF_Migration
Target Environment | NPC_TARGET_v2
Git Repository | https://github.com/jpziller/DataMigration
Commit / Branch | 31925f4c (feature/npc-fundraising-sample-recipe)
Scripts (as of this commit) | https://github.com/jpziller/DataMigration/tree/31925f4cd03106ebf2b0e2001da477830afbc1ef/sql/transformations
JIRA Project
Last Synced Log Id
Last Synced Source Ingestion Log Id
Stage | Object | Dependency | Status | Critical | Person Responsible | Begin Time | End Time | Execution Time | JIRA Ticket Link | Notes | Total Records | Success Records | Failed Records | Success Percent | Error Details
Pre-Migration Steps
Salesforce Config Changes | Confirm Email Deliverability setting (Setup > Email Administration > Deliverability) | None | Not Started | Yes
Salesforce Config Changes | Disable CPQ/Billing automation (or other managed-package automation) on target objects | None | Not Started | Yes
Salesforce Config Changes | Disable outbound automation that could email real contacts (workflow/Flow email alerts, approval processes) | None | Not Started | Yes
Pre Migration | Confirm target org/alias and auth mode for this pass | None | Not Started | Yes
Pre Migration | Run analyze-org-risk against in-scope objects | None | Not Started | No
Pre Migration | Take a backup/export of any target data being overwritten | None | Not Started | No
Source Download and Load Steps
Load Steps
Post-Migration Steps
Salesforce Config Changes | Re-enable Email Deliverability to its normal setting | None | Not Started | Yes
Salesforce Config Changes | Re-enable CPQ/Billing automation (or other managed-package automation) | None | Not Started | Yes
Salesforce Config Changes | Re-enable outbound automation disabled during Pre-Migration | None | Not Started | Yes
Post Migration | Spot-check row counts against source | None | Not Started | No
Post Migration | Notify stakeholders the load is complete | None | Not Started | No